## Milestones
Week | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | Deadline
ConOps Report | [107 empty] | 2022-02-09
Midterm Reprt (FSR, ICD, & Milestones) | [107 empty] | 2022-02-23
Midterm Presentations | [107 empty] | 2022-02-23
Project Update Presentation | [107 empty] | 2022-03-21
Final Presentation | [107 empty] | 2022-04-11
Final Demo | [107 empty] | 2022-04-29
Final Report | [107 empty] | 2022-04-30
Subsystems Timelines
Devboard/Programming
Machine Learning Optimization
Statistical Image Optimization
Stepper-motor Interface
Q/A Testing
Power Supply
Design Charging-Battery Interface
Design Redundancy System
Charging-Battery Assembly
Q/A Testing
Dev Board Mount
Measure and Design Mount Dimensions
Laser Cut Mounts
Design Standoffs (CAD)
3D Print Standoffs
Assembly & Mount
Stepper Motors
Design Motor Mounts (CAD)
3D Print Motor Mounts
Design Stepper Motor PWM interface
Q/A Testing
Imaging
Design Imager Mount (CAD)
3D Print Imager Mount
Design I/O Data Streaming Interface
Q/A Testing
Misc
Create Parts List
Create BOM
Finalize Parts Order
Place Parts Order

## Validation Plan
Task | Requirements | Desciption | Result | Owner
Devboard/Programming
Machine Learning Optimization | Can algorithm sort through at least 30 images and choose most focused? |  |  | Albin Myscich
Statistical Image Optimization | Is performance increased by stacking more than 10 images? |  |  | Albin Myscich
Stepper-motor Interface | Can interface move stepper motor interface by a specific margic? |  |  | Albin Myscich
Q/A Testing | All Tasks are passed in subsystem |  |  | Albin Myscich
Power Supply
Design Charging-Battery Interface | Is voltage at max after charging battery? |  |  | Camille Watson
Design Power Circuit System | Does each component theoretically recieve the necessary voltage and current to operate without damaging component or external parts of system? |  |  | Camille Watson
Implement Power Circuit | Does each component recieve measured voltage and current values in order to operate without damaging component or external parts of system? |  |  | Camille Watson
Charging-Battery Assembly | Does measurements assembly fit within constraints of the telescope? |  |  | Camille Watson
Q/A Testing | All Tasks are passed in subsystem |  |  | Albin Myscich
Dev Board Mount
Measure and Design Mount Dimensions | Do dimensions operate within the constraints of the telescope? |  |  | Camille Watson
Laser Cut Mounts | Are parts the same dimesions as designed? |  |  | Camille Watson
Design Standoffs (CAD) | Do dimensions of standoffs operate within the constraints of the telescope? |  |  | Camille Watson
3D Print Standoffs | Are the dimensions of parts accurate with the CAD design? |  |  | Camille Watson
Assembly & Mount | All Tasks are passed in subsystem |  |  | Albin Myscich
Stepper Motors
Design Motor Mounts (CAD) | Do dimensions operate within the constraints of the telescope? |  |  | Alonna Too-Chiobi
3D Print Motor Mounts | Are parts the same dimesions as designed? |  |  | Alonna Too-Chiobi
Design Stepper Motor PWM interface | Does motor operate on specific speeds and positions? |  |  | Alonna Too-Chiobi
Motor Quality | Does motor operate without damaging the motor mount and assembly subsystem? |  |  | Alonna Too-Chiobi
Q/A Testing | All Tasks are passed in subsystem |  |  | Albin Myscich
Imaging
Design Imager Mount (CAD) | Do dimensions operate within the constraints of the telescope? |  |  | Joey Basdeo
3D Print Imager Mount | Are parts the same dimesions as designed? |  |  | Joey Basdeo
Image Quality | Does image fit diesired image specifications (resolution, pixel width, and quantum effeciency) |  |  | Joey Basdeo
Design I/O Data Streaming Interface | Can imager recieve an image and transmit to Raspberry Pi under 5ms |  |  | Joey Basdeo
Q/A Testing | All Tasks are passed in subsystem |  |  | Albin Myscich
Misc
Create Parts List | Are all parts for each subsystem completed on initial list? |  |  | Albin Myscich
Create BOM | Does design fit measurement constraints of the telescope? |  |  | Albin Myscich
Create BOM | Is total amount of materials affordable with given budget? |  |  | Albin Myscich
Finalize Parts Order | Are parts correct in what is needed for each subsystem? |  |  | Albin Myscich
Place Parts Order | Will parts arrive in time to reach milestones and be validated according to plan? |  |  | Albin Myscich